## Gantt
PROJECT START: | 2022-10-01
ScholarSpace Gantt Chart: DEVELOPMENT PHASE
PROJECT LEAD: MUSA DUBE
KEY:
COMPLETE
IN-PROGRESS
NOT STARTED
|  |  | OCTOBER | [30 empty] | NOVEMBER
|  |  | 2022-10-01 | 2022-10-02 | 2022-10-03 | 2022-10-04 | 2022-10-05 | 2022-10-06 | 2022-10-07 | 2022-10-08 | 2022-10-09 | 2022-10-10 | 2022-10-11 | 2022-10-12 | 2022-10-13 | 2022-10-14 | 2022-10-15 | 2022-10-16 | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21 | 2022-10-22 | 2022-10-23 | 2022-10-24 | 2022-10-25 | 2022-10-26 | 2022-10-27 | 2022-10-28 | 2022-10-29 | 2022-10-30 | 2022-10-31 | 2022-11-01 | 2022-11-02 | 2022-11-03 | 2022-11-04 | 2022-11-05 | 2022-11-06 | 2022-11-07 | 2022-11-08 | 2022-11-09 | 2022-11-10 | 2022-11-11 | 2022-11-12 | 2022-11-13 | 2022-11-14 | 2022-11-15
TASK | START | END | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T
Frontend Phase 1: Design & Build Pages
1. Design steches for all the pages | 2022-10-01 | 2022-10-02 | bar: 2022-10-01 to 2022-10-02
2. Create design model | 2022-10-03 | 2022-10-10 | bar: 2022-10-03 to 2022-10-10
3. Convert designs to html and css | 2022-10-11 | 2022-10-12 | bar: 2022-10-11 to 2022-10-12
4. Integrate html & css into Angular: | 2022-10-13 | 2022-10-24 | bar: 2022-10-13 to 2022-10-24
a. Plan to integrate into Angular
b. Start Angular development
c. Profile-student, profile-recruiter, edit profile (recruiter and student)->
security, uplod-cv, add/edit-project, change-pass, delete-acc
d. Discover, upskilling, add-filters
e. notifications, tips, jobs, add/edit-job-post, notif-approved->
notif-closed, notif-interview, notif-badge
5. Test pages | 2022-10-25 | 2022-10-25 | bar: 2022-10-25
6. Design chat feature: | 2022-10-26 | 2022-10-26 | bar: 2022-10-26
a. Design chat model, convert to html/css, check responsiveness of page
b. integrate into Angular
Frontend Phase 2: Apply functionality to components | 2022-10-13 | 2022-10-31 | bar: 2022-10-13 to 2022-10-31
7. Plan how to implement functionality
8. roles, welcome, signup-recruiter, signup-student, interests, sign-in
9. discover, upskilling, add-filters
10. notifications, tips, jobs, add/edit-job-post, notif-approved ->
notif-closed, notif-interview, notif-badge
Frontend Phase 3: Testing and Conversion to PWA
11. Connect to HTTP-endpoint and test | 2022-11-01 | 2022-11-02
12. Convert to PWA and test | 2022-11-03 | 2022-11-04
Backend Phase 1: Design database model & Build it
0. Set up environmennt (github organisation, repo, branches) | 2022-10-09 | 2022-10-09 | bar: 2022-10-09
1. Lucidchart to build database model and create relationships | 2022-10-03 | 2022-10-03 | bar: 2022-10-03
2. Build database on firebase | 2022-10-10 | 2022-10-10 | bar: 2022-10-10
Backend Phase 2: Generate code snippets and Test
3. Generate content for upskilling and quiz, tips page | 2022-10-12 | 2022-10-16 | bar: 2022-10-12 to 2022-10-16
4. Generate code snippets for: | 13 Oxct | 2022-10-16 | bar: 2022-10-13 to 2022-10-16
a. Making indexes, inserting/adding data and documents, deletions, modifications
b. secure database access
c. Integrate firebase database with project
d. Data validation->
(conditions to verify that student emails are student emails, recruiter details) | bar: 2022-10-16
5. Convert Python image validation to Javascript | 2022-10-17 | 2022-10-17
Backend Phase 3: Create dummy project for testing
6.1 Create dummy pwa and wesbite | 2022-10-16 | 2022-10-19 | bar: 2022-10-19
6. Test code on a dummy project | 2022-10-20 | 2022-10-27 | bar: 2022-10-20 to 2022-10-27
7. Test: | 2022-10-28 | 2022-10-29 | bar: 2022-10-28 to 2022-10-29
a. hosting of dummy website
b. host dummy pwa via site installation buttons
c. test installation of dummy pwa on browser, desktop and mobile devices
Backend Phase 4: Hosting and testing | 2022-11-05 | 2022-11-06
7. Host website via firebase
8. Host application via website for installation (browser, desktop, mobile)